## Project Plan and Gantt
Project Name | Quản Lý Vé Máy Bay
Project Manager | Nguyễn Bá Anh Minh
Project Deliverable
Scope Statement:
Start Date | 2016-08-19
End Date | 2015-10-21
Overall Progress | 10%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Team | 2016-08-19 | 2016-08-19 | 0 | Complete
Agree on objectives | Team | 2016-08-19 | 2016-08-19 | 0 | Complete
Detailed Reqs. | Team | 2016-08-19 | 2016-08-21 | 2 | In-progress
Techincal Reqs. | Team | 2016-08-21 | 2016-08-23 | 2 | Not started
DB Development | Nguyễn Bá Anh Minh | 2016-08-23 | 2016-08-28 | 5 | Not started
Connect DB | Mai Thanh Phước | 2016-08-28 | 2016-09-02 | 5 | Not started
Insert/Update/Query | Phạm Minh Tú | 2016-09-02 | 2016-09-07 | 5 | Not started
API Development | Mai Thanh Phước | 2016-09-07 | 2016-09-14 | 7 | Not started
Function 1 | Nguyễn Bá Anh Minh | 2016-09-14 | 2016-09-22 | 8 | Not started
Function 2,… | Phạm Minh Tú | 2016-09-22 | 2016-09-30 | 8 | Not started
UI Client | Team | 2016-09-30 | 2016-10-06 | 6 | Not started
Testing | Team | 2016-10-06 | 2016-10-10 | 4 | Not started
Dev. Complete | Team | 2016-10-10 | 2016-10-15 | 5 | Not started
Hardware Config. | Team | 2016-10-15 | 2016-10-19 | 4 | Not started
System Testing | Team | 2016-10-19 | 2016-10-20 | 1 | Not started
Launch |  | 2016-10-20 | 2016-10-21 | 1

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address
Nguyễn Bá Anh Minh | Team leader, Devoloper | 1. Make the plan of the project. 2. Assign task for your member. 3. Analysis & design the system. 4. Code. 5. Write document
Phạm Minh Tú | Project Manager, Developer | 1. Design GUI/database. 2. Code. 3. Test | phamminhtu_it@yahoo.com
Mai Thanh Phước | Project Manager, Developer | 1. Design GUI/database. 2. Code. 3. Test

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience